## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Setup Spring Boot & React Vite Project Foundation | Configure the Spring Boot backend, React Vite frontend, Maven Wrapper, and standard module-based folder structure. | Task-01 | https://github.com/BTHL-123/clinic-management-system/pull/1 | Closed | binhtranqs | 2026-05-13 07:58 | 2026-05-20 | Iteration 1 (M1) | WP, 3_Done | Auth & Security
PostgreSQL Datasource & Database Schema Connection | Configure the PostgreSQL database connection in application.yml, supporting environment variables and an H2 test profile. | Task-02 | https://github.com/BTHL-123/clinic-management-system/pull/2 | Closed | binhtranqs | 2026-05-13 08:46 | 2026-05-20 | Iteration 1 (M1) | WP, 3_Done | Auth & Security
Stateless Security & JWT Authentication Core | Configure stateless Spring Security, JWT authentication filter, BCrypt password encoder, and Unauthorized/AccessDenied error handling. | Task-03 | https://github.com/BTHL-123/clinic-management-system/pull/12 | Closed | binhtranqs | 2026-05-19 15:30 | 2026-05-20 | Iteration 1 (M1) | Feature, 3_Done | Auth & Security
Patient Self-Registration API & UI Page | Develop the POST /api/auth/register endpoint that automatically creates an accompanying patient profile, along with the /register screen. | Task-04 | https://github.com/BTHL-123/clinic-management-system/pull/12 | Closed | binhtranqs | 2026-05-19 15:30 | 2026-05-20 | Iteration 1 (M1) | Feature, 3_Done | Auth & Security
User Authentication Login API & UI Page | Develop the POST /api/auth/login endpoint returning a JWT Access Token & Refresh Token, along with the /login screen. | Task-05 | https://github.com/BTHL-123/clinic-management-system/pull/12 | Closed | binhtranqs | 2026-05-19 15:30 | 2026-05-20 | Iteration 1 (M1) | Feature, 3_Done | Auth & Security
User Logout API & Client Auth State Cleanup | Develop the POST /api/auth/logout endpoint and clear tokens in the client-side AuthContext. | Task-06 | https://github.com/BTHL-123/clinic-management-system/pull/12 | Closed | binhtranqs | 2026-05-19 15:30 | 2026-05-20 | Iteration 1 (M1) | Task, 3_Done | Auth & Security
Restore Current User Session Profile | Develop the GET /api/auth/me endpoint to restore the user session and display user info in the Header. | Task-07 | https://github.com/BTHL-123/clinic-management-system/pull/12 | Closed | binhtranqs | 2026-05-19 15:30 | 2026-05-20 | Iteration 1 (M1) | Task, 3_Done | Auth & Security
User Management CRUD APIs & Admin Page | Build APIs for listing, creating, updating, and locking/unlocking accounts, along with the /dashboard/users management screen. | Task-08 | https://github.com/BTHL-123/clinic-management-system/pull/12 | Closed | binhtranqs | 2026-05-19 15:30 | 2026-05-20 | Iteration 1 (M1) | Feature, 3_Done | User Management
Role & Permission Management UI | Build the system role catalog, permission list, and the /dashboard/security permission-assignment screen. | Task-09 | https://github.com/BTHL-123/clinic-management-system/pull/12 | Closed | binhtranqs | 2026-05-19 15:30 | 2026-05-20 | Iteration 1 (M1) | Feature, 3_Done | Role & Security Management
Admin Dashboard Base Layout & Navigation | Basic dashboard layout including Sidebar, Header, ProtectedRoute, and keyboard-shortcut navigation. | Task-10 | https://github.com/BTHL-123/clinic-management-system/pull/12 | Closed | binhtranqs | 2026-05-19 15:30 | 2026-05-20 | Iteration 1 (M1) | WP, 3_Done | Auth & Security
Department Management CRUD APIs & Page | Develop the Entity, Repository, Service, Controller, and UI for managing the clinic's department catalog. | Task-11 | https://github.com/BTHL-123/clinic-management-system/pull/13 | Closed | LuuHoa206 | 2026-05-19 19:19 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Department Management
Doctor Management Catalog & CRUD | Develop the module for managing doctor information, assigning departments, filtering, and searching doctors. | Task-12 | https://github.com/BTHL-123/clinic-management-system/pull/14 | Closed | LuuHoa206 | 2026-05-19 20:35 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Doctor & Staff Management
Patient Demographic Profile & Management | Manage patient demographic data, patient ID, address, phone number, and emergency contact information. | Task-13 | https://github.com/BTHL-123/clinic-management-system/pull/14 | Closed | LuuHoa206 | 2026-05-19 21:21 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Patient Management
Staff Management System Implementation | Develop APIs and UI for managing medical staff (receptionists, pharmacists, lab technicians). | Task-14 | https://github.com/BTHL-123/clinic-management-system/pull/14 | Closed | LuuHoa206 | 2026-05-20 14:36 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Doctor & Staff Management
Patient Profile View & Medical Context Page | Design the patient profile detail page, displaying health insurance information and interaction history. | Task-15 | https://github.com/BTHL-123/clinic-management-system/pull/14 | Closed | LuuHoa206 | 2026-05-20 15:06 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Patient Management
Doctor Professional Profile & Qualifications Page | Screen for viewing and editing detailed doctor information: qualifications, academic titles/degrees, year of birth, and hometown. | Task-16 | https://github.com/BTHL-123/clinic-management-system/pull/14 | Closed | LuuHoa206 | 2026-05-20 15:44 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Doctor & Staff Management
Medical Service Management & Pricing Setup | Develop the catalog of examination services, medical service types, service fees, and applicable status. | Task-17 | https://github.com/BTHL-123/clinic-management-system/pull/14 | Closed | anhtrinh05 | 2026-05-20 15:10 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Department Management
Doctor Schedule Registration & Shift Management | Allow doctors to register weekly/monthly work shifts and manage their working clinic rooms. | Task-18 | https://github.com/BTHL-123/clinic-management-system/pull/27 | Closed | tannade180602 | 2026-05-20 14:30 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Doctor Schedule & Slot Management
Automatic Doctor Schedule Slot Generation API | Build the algorithm that automatically generates appointment slots from doctors' work shifts. | Task-19 | https://github.com/BTHL-123/clinic-management-system/pull/27 | Closed | tannade180602 | 2026-05-21 12:06 | 2026-05-26 | Iteration 2 (M2) | Task, 3_Done | Doctor Schedule & Slot Management
Available Doctor Slot Query & Filtering | API and UI for querying available appointment slots by date, doctor, and department. | Task-20 | https://github.com/BTHL-123/clinic-management-system/pull/26 | Closed | tannade180602 | 2026-05-21 12:12 | 2026-05-26 | Iteration 2 (M2) | Task, 3_Done | Doctor Schedule & Slot Management
Temporary Slot Locking Mechanism during Booking | Develop a feature to temporarily lock an appointment slot for a set duration to prevent double booking. | Task-21 | https://github.com/BTHL-123/clinic-management-system/pull/25 | Closed | tannade180602 | 2026-05-21 12:13 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Doctor Schedule & Slot Management
Google OAuth2 Single Sign-On Integration | Integrate Google account sign-in, automatically linking email accounts and issuing a JWT. | Task-22 | https://github.com/BTHL-123/clinic-management-system/pull/28 | Closed | binhtranqs | 2026-05-21 11:18 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Auth & Security
Consultation Entity & Service Initialization | Initialize the Consultation Entity, Repository, and Service to handle the doctor's examination business logic. | Task-23 | https://github.com/BTHL-123/clinic-management-system/pull/67 | Closed | lonkdemon | 2026-05-20 23:26 | 2026-06-03 | Iteration 3 (M3) | Task, 3_Done | Consultation & Medical Records
Electronic Health Record (EHR) Module Setup | Set up the data structure and API for managing electronic health records, storing medical history and reason for visit. | Task-24 | https://github.com/BTHL-123/clinic-management-system/pull/67 | Closed | lonkdemon | 2026-05-20 23:37 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Consultation & Medical Records
Vital Signs Recording & Tracking Setup | Set up the module for recording vital signs (pulse, temperature, blood pressure, weight, height, BMI). | Task-25 | https://github.com/BTHL-123/clinic-management-system/pull/67 | Closed | lonkdemon | 2026-05-20 23:19 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Vital Signs
Lab Test Order Management Setup | Configure the medical lab test catalog and the lab-test ordering flow during a consultation. | Task-26 | https://github.com/BTHL-123/clinic-management-system/pull/67 | Closed | lonkdemon | 2026-05-20 23:22 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Lab Test Management
Medicine Catalog & Master Data Setup | Build the medicine catalog table: active ingredients, dosage strength, route of administration, unit, and selling price. | Task-27 | https://github.com/BTHL-123/clinic-management-system/pull/67 | Closed | lonkdemon | 2026-05-20 23:22 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Medicine Catalog & Inventory
Invoice Management & Billing CRUD APIs | Develop APIs to calculate total costs for examination, lab tests, and prescriptions, and to generate payment invoices. | Task-28 | https://github.com/BTHL-123/clinic-management-system/pull/17 | Closed | anhtrinh05 | 2026-05-20 18:55 | 2026-06-16 | Iteration 4 (M4) | Feature, 3_Done | Invoice & Payment Processing
Cash Payment Confirmation & Receipt Generation | Develop the cash payment confirmation feature at the counter for receptionists and print a receipt. | Task-29 | https://github.com/BTHL-123/clinic-management-system/pull/17 | Closed | anhtrinh05 | 2026-05-20 20:38 | 2026-06-16 | Iteration 4 (M4) | Feature, 3_Done | Invoice & Payment Processing
Patient Online Appointment Booking UI Flow | Develop the patient appointment booking UI, allowing selection of department, doctor, date, and time slot. | Task-30 | https://github.com/BTHL-123/clinic-management-system/pull/40 | Closed | binhtranqs | 2026-05-21 14:03 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Appointment Booking & History
Queue Ticket Issuance & Check-in Management | Develop the automatic queue-ticket issuance system for patients checking in at the counter and manage the waiting queue. | Task-31 | https://github.com/BTHL-123/clinic-management-system/pull/54 | Closed | binhtranqs | 2026-05-29 16:02 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Queue Management & Check-in
Doctor Today's Patient List Dashboard | Dashboard displaying the list of checked-in patients waiting for the doctor's examination that day. | Task-32 | https://github.com/BTHL-123/clinic-management-system/pull/58 | Closed | binhtranqs | 2026-05-29 18:08 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Consultation & Medical Records
Start Consultation Workflow Integration | Feature allowing the doctor to start a consultation, call the patient's queue number, and open the examination record. | Task-33 | https://github.com/BTHL-123/clinic-management-system/pull/52 | Closed | binhtranqs | 2026-05-30 22:58 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Consultation & Medical Records
Create & Update Medical Record Entry | Record clinical symptoms, preliminary diagnosis, confirmed diagnosis, and the doctor's advice. | Task-34 | https://github.com/BTHL-123/clinic-management-system/pull/65 | Closed | binhtranqs | 2026-05-30 22:58 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Consultation & Medical Records
Vital Signs Entry during Patient Examination | Screen for directly entering vital signs while the doctor performs the examination. | Task-35 | https://github.com/BTHL-123/clinic-management-system/pull/55 | Closed | binhtranqs | 2026-05-30 22:58 | 2026-06-03 | Iteration 3 (M3) | Task, 3_Done | Vital Signs
Create Clinical Lab Test Request | Doctor selects lab tests from the catalog and creates a lab test request for the patient. | Task-36 | https://github.com/BTHL-123/clinic-management-system/pull/66 | Closed | binhtranqs | 2026-05-30 22:58 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Lab Test Management
Accept Lab Request by Lab Technician | Lab technician UI for accepting the test request and changing its status from Pending to In Progress. | Task-37 | https://github.com/BTHL-123/clinic-management-system/pull/57 | Closed | binhtranqs | 2026-05-30 22:58 | 2026-06-03 | Iteration 3 (M3) | Task, 3_Done | Lab Test Management
Create Lab Result Entry & File Upload | Enter lab result data, upload result files, and input the lab technician's medical conclusion. | Task-38 | https://github.com/BTHL-123/clinic-management-system/pull/69 | Closed | binhtranqs | 2026-05-31 10:13 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Lab Test Management
Prescription Entry & Medication Assignment | Doctor selects medicine from the catalog and enters quantity, route (oral/injection), frequency per day, and timing. | Task-39 | https://github.com/BTHL-123/clinic-management-system/pull/71 | Closed | binhtranqs | 2026-05-31 10:13 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Prescription & Drug Interaction
Drug Interaction Safety Alert Integration | Integrate a drug-interaction check API that automatically shows red/yellow warnings when conflicting drugs are prescribed together. | Task-40 | https://github.com/BTHL-123/clinic-management-system/pull/72 | Closed | binhtranqs | 2026-05-31 12:28 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Prescription & Drug Interaction
Email OTP Verification Code Authentication | Develop the service for sending an email OTP verification code for account verification and password recovery. | Task-41 | https://github.com/BTHL-123/clinic-management-system/pull/41 | Closed | binhtranqs | 2026-05-25 21:20 | 2026-05-26 | Iteration 2 (M2) | Feature, 3_Done | Auth & Security
Patient Medical History & Consultation Timeline | UI for viewing the consultation history timeline, past diagnoses, past prescriptions, and lab results. | Task-42 | https://github.com/BTHL-123/clinic-management-system/pull/43 | Closed | LuuHoa206 | 2026-05-27 20:09 | 2026-06-03 | Iteration 3 (M3) | Feature, 3_Done | Patient Management
Online Payment Gateway Integration (SePay / QR Code) | Integrate the SePay service to automatically generate a bank-transfer QR code and a webhook confirming invoice status. | Task-43 | https://github.com/BTHL-123/clinic-management-system/pull/35 | Closed | binhtranqs | 2026-05-24 20:11 | 2026-06-16 | Iteration 4 (M4) | Feature, 3_Done | Invoice & Payment Processing
Medicine Inventory & Stock Batch Management | Manage medicine inventory, suppliers, production batches, expiry dates, and stock in/out functions. | Task-44 | https://github.com/BTHL-123/clinic-management-system/pull/36 | Closed | binhtranqs | 2026-05-24 20:39 | 2026-06-16 | Iteration 4 (M4) | Feature, 3_Done | Medicine Catalog & Inventory
AI Triage & Specialty Suggestion Chatbot | Integrate an AI Chatbot (Gemini / Python service) for initial health consultation and department recommendation. | Task-45 | https://github.com/BTHL-123/clinic-management-system/pull/37 | Closed | binhtranqs | 2026-05-24 21:40 | 2026-06-16 | Iteration 4 (M4) | Feature, 3_Done | AI Chatbot & Clinical Support
Clinic Revenue & Operational Analytics Reports | Reports on clinic revenue statistics, number of visits over time, and medicine stock-out statistics. | Task-46 | https://github.com/BTHL-123/clinic-management-system/pull/76 | Closed | LuuHoa206 | 2026-06-02 18:02 | 2026-06-16 | Iteration 4 (M4) | Feature, 3_Done | Reports & Analytics
Pharmacist Dispensing Queue & Medication Processing | Pharmacist screen for reviewing paid prescriptions, checking them, and confirming dispensing/stock-out. | Task-47 | https://github.com/BTHL-123/clinic-management-system/pull/80 | Closed | LuuHoa206 | 2026-06-03 18:00 | 2026-06-16 | Iteration 4 (M4) | Feature, 3_Done | Prescription Dispensing
Receptionist Walk-in Patient Queue Optimization | Improve the walk-in patient check-in UI, quick profile lookup, and examination queueing. | Task-48 | https://github.com/BTHL-123/clinic-management-system/pull/86 | Closed | LuuHoa206 | 2026-06-04 09:45 | 2026-06-16 | Iteration 4 (M4) | Feature, 3_Done | Queue Management & Check-in
System Audit Trail Logs & Activity Viewer | Screen for Admin & Auditor to view detailed activity logs, login history, and data operations. | Task-49 | https://github.com/BTHL-123/clinic-management-system/pull/92 | Closed | binhtranqs | 2026-06-05 17:11 | 2026-07-22 | Iteration 5 (M5) | Feature, 3_Done | Audit Log & System Settings
Global System Settings & Clinic Configuration | System configuration page: clinic information, default examination time, and notification settings. | Task-50 | https://github.com/BTHL-123/clinic-management-system/pull/93 | Closed | binhtranqs | 2026-06-05 17:46 | 2026-07-22 | Iteration 5 (M5) | Feature, 3_Done | Audit Log & System Settings
Global Toast Notification & Error Interceptor | Catch API errors globally via an Axios Interceptor and display professional toast warning notifications. | Task-51 | https://github.com/BTHL-123/clinic-management-system/pull/90 | Closed | binhtranqs | 2026-06-05 15:15 | 2026-07-22 | Iteration 5 (M5) | Task, 3_Done | Auth & Security
Doctor Examination UI/UX Layout Modernization | Redesign the entire doctor's consultation screen with a modern, smooth, and user-friendly layout. | Task-52 | https://github.com/BTHL-123/clinic-management-system/pull/96 | Closed | LuuHoa206 | 2026-06-08 13:22 | 2026-07-22 | Iteration 5 (M5) | Task, 3_Done | Consultation & Medical Records
Pharmacist & Lab Tech Master-Detail UI Redesign | Restructure the Pharmacist and Lab Technician UI into a modern Master-Detail design. | Task-53 | https://github.com/BTHL-123/clinic-management-system/pull/98 | Closed | LuuHoa206 | 2026-06-09 16:45 | 2026-07-22 | Iteration 5 (M5) | Task, 3_Done | Prescription Dispensing
Fix Walk-in Queue Reference Error & Doctor Creation | Fix the fetchData ReferenceError in the Receptionist UI and adjust permissions for creating doctor accounts. | Task-54 | https://github.com/BTHL-123/clinic-management-system/pull/110 | Closed | LuuHoa206 | 2026-06-14 20:13 | 2026-07-22 | Iteration 5 (M5) | Defect, 3_Done | Queue Management & Check-in
Landing Page Redesign & Real Doctor Catalog Sync | Upgrade the clinic's homepage/landing page UI and remove mock doctor data. | Task-55 | https://github.com/BTHL-123/clinic-management-system/pull/145 | Closed | LuuHoa206 | 2026-07-20 18:32 | 2026-07-22 | Iteration 5 (M5) | Feature, 3_Done | Appointment Booking & History
Admin Dashboard Revenue Analytics Chart Upgrade | Add detailed daily/monthly revenue analytics charts to the Admin dashboard. | Task-56 | https://github.com/BTHL-123/clinic-management-system/pull/145 | Closed | LuuHoa206 | 2026-07-20 18:32 | 2026-07-22 | Iteration 5 (M5) | Feature, 3_Done | Reports & Analytics
Role-Aware Login Redirect Bug Fix | Fix the post-login redirect bug for specific user roles. | Task-57 | https://github.com/BTHL-123/clinic-management-system/pull/146 | Closed | LuuHoa206 | 2026-07-20 18:47 | 2026-07-22 | Iteration 5 (M5) | Defect, 3_Done | Auth & Security
Production VPS Docker Containerization & Deployment Handoff | Create the docker-compose.yml file and write handoff documentation for deploying the system on a VPS server. | Task-58 | https://github.com/BTHL-123/clinic-management-system/pull/148 | Closed | LuuHoa206 | 2026-07-20 20:14 | 2026-07-22 | Iteration 5 (M5) | WP, 3_Done | Deployment & Containerization
Doctor Notification Theme Color & Header Sync Fix | Synchronize the notification UI color theme and header design for the Doctor role. | Task-59 | https://github.com/BTHL-123/clinic-management-system/pull/140 | Closed | tannade180602 | 2026-07-21 16:19 | 2026-07-22 | Iteration 5 (M5) | Defect, 3_Done | Consultation & Medical Records